## Sheet1
List Name | Name | Start Date | End Date | Detailed Description
Phase 1: Foundation | Set up GitHub repo and initialize Streamlit app | 2025-07-01 | 2025-07-02 | Create GitHub repo, add .gitignore, set up folders and main.py for Streamlit.
Phase 1: Foundation | Build basic UI layout | 2025-07-03 | 2025-07-04 | Design sidebar and main layout area using Streamlit for filters, KPIs, and charts.
Phase 1: Foundation | Fetch and display EIA data | 2025-07-05 | 2025-07-06 | Use EIA API key to fetch electricity price data and display a basic line chart.
Phase 2: Data Integration | Add date range filter | 2025-07-07 | 2025-07-08 | Add Streamlit date inputs or select boxes to control the timeframe shown.
Phase 2: Data Integration | Add granularity toggle (monthly / yearly) | 2025-07-09 | 2025-07-10 | Add radio button or select box to toggle granularity.
Phase 2: Data Integration | Enable state/sector filters | 2025-07-11 | 2025-07-12 | Add multiselect filters for state and end-use sector.
Phase 2: Data Integration | Calculate and display KPIs | 2025-07-13 | 2025-07-14 | Compute and show average price, max price, and count of months.
Phase 3: Feature Enhancements | Improve layout using Streamlit columns | 2025-07-15 | 2025-07-16 | Use `st.columns` to structure the layout for a better UX.
Phase 3: Feature Enhancements | Add natural language insight generator | 2025-07-17 | 2025-07-18 | Add simple NLP logic to summarize trends in plain language.
Phase 3: Feature Enhancements | Add tooltip and hover labels for charts | 2025-07-19 | 2025-07-20 | Switch to Plotly to enable interactive tooltips.
Phase 3: Feature Enhancements | Add CSV export/download option | 2025-07-21 | 2025-07-22 | Let users download filtered data using `st.download_button`.
Phase 4: Forecasting and Analytics | Integrate Prophet for time series forecasting | 2025-07-23 | 2025-07-24 | Add Prophet model using EIA data to forecast prices.
Phase 4: Forecasting and Analytics | Add toggle to show/hide forecast | 2025-07-25 | 2025-07-26 | Add a Streamlit toggle to conditionally show the forecast chart.
Phase 4: Forecasting and Analytics | Display forecasted chart alongside actuals | 2025-07-27 | 2025-07-28 | Overlay forecast and historical prices in a dual-line chart.
Phase 4: Forecasting and Analytics | Add natural language summary of forecast | 2025-07-29 | 2025-07-30 | Summarize forecast in plain language, e.g., 'Prices expected to rise.'
Phase 5: Deployment and Monetization | Create requirements.txt and secrets.toml | 2025-07-31 | 2025-08-01 | List dependencies and securely add API keys for deployment.
Phase 5: Deployment and Monetization | Deploy to Streamlit Cloud (private or public) | 2025-08-02 | 2025-08-03 | Connect to GitHub and deploy app via Streamlit Cloud.
Phase 5: Deployment and Monetization | Set up a project README on GitHub | 2025-08-04 | 2025-08-05 | Write a clear README with instructions, screenshots, and features.
Phase 5: Deployment and Monetization | Research monetization (ads, premium access, consulting) | 2025-08-06 | 2025-08-07 | Explore how the app can generate revenue responsibly.
Phase 6: Forecasting Optimization | Tune Prophet hyperparameters (seasonality, changepoints, holidays) | 2025-07-26 | 2025-07-27 | Optimize Prophet's forecasting accuracy by adjusting seasonality settings, changepoints, and holiday effects.
Phase 6: Forecasting Optimization | Test model performance across all U.S. states | 2025-07-28 | 2025-07-29 | Apply and evaluate the forecast model for each U.S. state to ensure broad applicability and accuracy.
Phase 6: Forecasting Optimization | Add model evaluation metrics (MAPE, RMSE) | 2025-07-30 | 2025-07-31 | Display forecasting error metrics like MAPE or RMSE to evaluate model performance.
Phase 6: Forecasting Optimization | Allow users to toggle forecast confidence intervals | 2025-08-01 | 2025-08-02 | Let users show or hide Prophet's prediction uncertainty ranges on the graph.
Phase 7: Built-in Chat Assistant | Build chat interface in Streamlit using st.chat_input and st.chat_message | 2025-08-03 | 2025-08-04 | Create an interactive chat window in the app for asking questions and interacting with the data.
Phase 7: Built-in Chat Assistant | Enable chatbot to answer app-specific questions (e.g. average price by state) | 2025-08-05 | 2025-08-06 | Enable the assistant to respond to user queries about energy prices using the dataset.
Phase 7: Built-in Chat Assistant | Connect chatbot to filtered data context | 2025-08-07 | 2025-08-08 | Ensure chatbot answers are based on the current filtered dataset in the app.
Phase 7: Built-in Chat Assistant | Add dynamic suggestions or prompt buttons in chat | 2025-08-09 | 2025-08-10 | Provide buttons or prompts like 'Show Forecast' or 'Compare States' for user convenience.
Phase 8: External Data Fusion | Integrate weather forecast API (e.g., OpenWeatherMap) | 2025-08-11 | 2025-08-12 | Fetch external weather data for each state to correlate with pricing trends.
Phase 8: External Data Fusion | Join weather and pricing data by state and date | 2025-08-13 | 2025-08-14 | Merge weather and pricing datasets to analyze combined impacts.
Phase 8: External Data Fusion | Add exogenous regressors (weather) to Prophet model | 2025-08-15 | 2025-08-16 | Incorporate weather data as external variables in the forecast model.
Phase 8: External Data Fusion | Integrate news sentiment API and display headline insights | 2025-08-17 | 2025-08-18 | Show energy-related news headlines or summaries to provide external market context.
Phase 9: Real-Time ISO Data | Research ISO APIs (PJM, CAISO, ERCOT) | 2025-08-19 | 2025-08-20 | Identify and evaluate available ISO APIs for pricing, load, and real-time data.
Phase 9: Real-Time ISO Data | Integrate ISO real-time price and demand data | 2025-08-21 | 2025-08-22 | Pull and display real-time energy prices and demand from ISO feeds.
Phase 9: Real-Time ISO Data | Visualize ISO prices on a map dashboard | 2025-08-23 | 2025-08-24 | Show ISO pricing geographically via a U.S. map view.
Phase 9: Real-Time ISO Data | Use ISO + weather data in new forecasting model | 2025-08-25 | 2025-08-26 | Extend the forecast model to include ISO and weather data inputs.
Phase 10: Testing and Performance | Test edge cases (missing data, date ranges, filters) | 2025-08-27 | 2025-08-28 | Verify app stability and accuracy when data is incomplete or filtered unusually.
Phase 10: Testing and Performance | Run performance test for multi-state selection | 2025-08-29 | 2025-08-30 | Test app speed and behavior when visualizing multiple states simultaneously.
Phase 10: Testing and Performance | Log errors and create simple debug output | 2025-08-31 | 2025-09-01 | Add internal logging to help catch and troubleshoot issues.
Phase 10: Testing and Performance | Create bug/feature tracking dashboard (Google Sheets or Notion) | 2025-09-02 | 2025-09-03 | Track issues and ideas using an external tool like Notion or Sheets.
Phase 11: Premium App Features | Add state comparison (multi-line chart + KPIs) | 2025-09-04 | 2025-09-05 | Enable users to compare multiple states side by side with charts and stats.
Phase 11: Premium App Features | Create national heatmap by price levels | 2025-09-06 | 2025-09-07 | Visualize energy price levels across the U.S. via a color-coded heatmap.
Phase 11: Premium App Features | Simulate appliance usage and show bill impact by state | 2025-09-08 | 2025-09-09 | Let users simulate electricity cost by appliance usage in their state.
Phase 11: Premium App Features | Add event annotations to graphs (e.g., Texas freeze) | 2025-09-10 | 2025-09-11 | Mark historical events on graphs for context and insight.
Phase 12: Smart Automation and UX | Enable weekly/daily summary generation with trends | 2025-09-12 | 2025-09-13 | Auto-generate and display weekly or daily summaries of energy trends.
Phase 12: Smart Automation and UX | Set up auto-refresh of data weekly | 2025-09-14 | 2025-09-15 | Automate data fetching and caching to ensure users always see updated info.
Phase 12: Smart Automation and UX | Save user preferences for states and filters | 2025-09-16 | 2025-09-17 | Allow returning users to retain their filter selections between sessions.
Phase 12: Smart Automation and UX | Add mobile-friendly layout with tabbed navigation | 2025-09-18 | 2025-09-19 | Optimize layout for mobile devices with tab-based navigation.
Phase 13: Monetization Strategy | Add user login to save states and comparison settings | 2025-09-20 | 2025-09-21 | Enable user accounts to store preferences and settings.
Phase 13: Monetization Strategy | Explore freemium pricing model (e.g. unlock full state list) | 2025-09-22 | 2025-09-23 | Introduce premium features such as unlimited states or advanced tools.
Phase 13: Monetization Strategy | Add usage limit for free users | 2025-09-24 | 2025-09-25 | Cap data or features for free users to encourage upgrade.
Phase 13: Monetization Strategy | Enable API access with usage key | 2025-09-26 | 2025-09-27 | Provide API access to your app’s data with usage tracking.
Phase 14: Final Packaging & Launch | Add onboarding tutorial for first-time users | 2025-09-28 | 2025-09-29 | Guide new users through the app with helpful tooltips and instructions.
Phase 14: Final Packaging & Launch | Package as mobile web app or PWA | 2025-09-30 | 2025-10-01 | Wrap the app in a PWA format to allow install on mobile devices.
Phase 14: Final Packaging & Launch | Launch on Play Store / TestFlight | 2025-10-02 | 2025-10-03 | Distribute the app via mobile platforms for wide reach.
Phase 14: Final Packaging & Launch | Promote via LinkedIn / GitHub / Product Hunt | 2025-10-04 | 2025-10-05 | Market the app via professional platforms and app discovery sites.